## Identified and Estimated Risks
Estiamted Risk
RIS ID | Risks | Category | Probability | Impact | RMMM
RIS1 | Communication failure | ST | 70 | 1 | See RIS1 Form
RIS2 | Management | ST | 70 | 1 | See RIS2 Form
RIS3 | Lack of experience implementing the technology | TE | 100 | 1 | See RIS3 Form
RIS4 | Security risk | DE | 30 | 2 | See RIS4 Form
RIS5 | Time constraint with team development | ST | 60 | 2 | See RIS5 Form
RIS6 | Not able to follow the prototype | ST | 40 | 2 | See RIS6 Form
RIS7 | Requirement change by the customer | CU | 20 | 3 | See RIS7 Form
RIS8 | End user expectation | BU | 20 | 3 | See RIS8 Form
RIS9 | The needs of a database | DE | 10 | 2 | See RIS9 Form
RIS10 | User login | BU | 10 | 3 | See RIS10 Form

## RIS1
Risk information sheet
Risk ID: RIS1 | Date: 1/31/2020 | Prob: 70% | Impact: High
Description: Ineffective communication between end user and team
Refinement/context: End user might use vague language that makes it hard for the team to design a plan.
Mitigation/monitoring: Meet with the the end user regularly and discuss the desired features of the product.
Management/contingency plan/trigger: The team will go over what they had previously discussed with the client and if there are any concerns set up in person meetings with the end user.
Current status: As of 1/31/2020 we have met with our client twice to discuss the desired feature of our app.
Originator: B. Dempsey, L. Johnson, O. Ilano, A. Samuel, S. Singh |  | Assigned: A. Samuel

## RIS2
Risk information sheet
Risk ID: RIS2 | Date: 01/31/2020 | Prob: 70% | Impact: High
Description: Poor management can result poor development team performance and bad project productivity.
Refinement/context: The manager is not willing to pay attention to what the development team has to say. The manager is having a bad attitude towards the development team. Poor planning and organization.
Mitigation/monitoring: Keep tasks organized and understand the timeline. Make sure to do preliminary planning. Listen carefully to the development team, customer, and stakeholders. Pay attention to the details and be respectful towards everyone.
Management/contingency plan/trigger: The development team will let the manager know if they have not been satisfied with the management. If the manager has not done anything to make the management better after being notified, then the higher up, customer, and stakeholders should be notified of what is going on. Reevaluate if a replacement of a manager is needed.
Current status: As of 01/31/2020, the development team is satisfied with the management.
Originator: B. Dempsey, L. Johnson, O. Ilano, A. Samuel, S. Singh |  | Assigned: O. Ilano

## RIS3
Risk information sheet
Risk ID: RIS3 | Date: 1/31/2020 | Prob: 100% | Impact: high
Description: We do not have very much experience with the technology being proposed to implement this project.
Refinement/context: Being that we are students, we have little experience with the technology, or this is our first exposure to the technology at all.
Mitigation/monitoring: We are all in the process of learning the technology in general while we work to implement the project requirements.
Management/contingency plan/trigger: We have all individually downloaded the required software and are working in our own time to understand it.
Current status: 1/31/20: Mitigation steps initiated
Originator: B. Dempsey, L. Johnson, O. Ilano, A. Samuel, S. Singh |  | Assigned: B. Dempsey

## RIS4
Risk information sheet
Risk ID: RIS4 | Date: 1/31/2020 | Prob: 30% | Impact: High
Description: The database should be implemented by keeping in mind all the security risk
Refinement/context: If someone gets access to the database, the data can be misused.
Mitigation/monitoring: We are developing the application keeping the security of the application in mind.
Management/contingency plan/trigger:
Current status: As of 1/31/2020: It will be initiated with the development of application.
Originator: B. Dempsey, L. Johnson, O. Ilano, A. Samuel, S. Singh |  | Assigned: S. Singh

## RIS5
Risk information sheet
Risk ID: RIS5 | Date: 1/31/2020 | Prob: 60% | Impact: High
Description: Dedicating time to the project is crucial to the success of the project. With possible time restraints, there is a risk of failure.
Refinement/context: 1.) With other classes and personal responsibilities to focus on, it is a possible risk that the developers will not have enough time to focus on the project. 2.) Agile development is a new technique for the developers, so learning to dedicate the proper time to the project might be difficult.
Mitigation/monitoring: 1.) Assign tasks and deadlines to the developers to keep them focused. 2.) Incentivize the developers to meet deadlines by enforcing the team slacker policy.
Management/contingency plan/trigger: If the development team cannot make enough time to meet the requirements of the current sprint, a meeting will be conducted to rework a new schedule for the team to ensure that everyone can accomplish tasks within the given timeframe. Trigger: If tasks are not up-to-date and on track by the middle of the sprint (2/15/2020)
Current status: The team has set a certain time to dedicate to the project.
Originator: B. Dempsey, L. Johnson, O. Ilano, A. Samuel, S. Singh |  | Assigned: O. Ilano

## RIS6
Risk information sheet
Risk ID: RIS6 | Date: 1/31/2020 | Prob: 40% | Impact: Medium
Description: The development team was given a prototype by the product owner and instructed to follow it as closely as possible
Refinement/context: 1.) The prototype may be more difficult to implement than originally expected 2.) The development team may find a new layout that they find more organized and functional than the original prototype
Mitigation/monitoring: 1.) The development team will always keep the prototype model in mind when creating the application 2.) The development team will build the prototype and then work implement design and features afterward.
Management/contingency plan/trigger: If the team feels that they cannot follow the prototype, or run into any issues with the given prototype, a meeting will be scheduled with the product owner to discuss a possible new prototype to follow. Trigger: If the team is not able to follow the prototype after the first week of the sprint (2/9/2020)
Current status: The team is focused on following the prototype.
Originator: B. Dempsey, L. Johnson, O. Ilano, A. Samuel, S. Singh |  | Assigned: L. Johnson

## RIS7
Risk information sheet
Risk ID: RIS7 | Date: 1/31/2020 | Prob: 20% | Impact: Medium
Description: The requirements given by the product owner for the application may change over the course of development.
Refinement/context: 1.) The product owner may discover a new way of implementing the application 2.) The product owner may request a new feature to be implemented in the application
Mitigation/monitoring: 1.) The team will practice agile development and be flexible and prepared to accommodate the customer's requests. 2.) The development team will stay on or ahead of schedule in order to give time for requirement changes.
Management/contingency plan/trigger: The development team will meet with the product owner and create a product backlog for the upcoming sprint in order to ensure the customer will be satisfied. Trigger: If the product owner announces a change in requirements
Current status: No changes as of 01/31/2020
Originator: B. Dempsey, L. Johnson, O. Ilano, A. Samuel, S. Singh |  | Assigned: L. Johnson

## RIS8
Risk information sheet
Risk ID: RIS8 | Date: 01/31/2020 | Prob: 20% | Impact: Low
Description: The application should meet the demands of end user.
Refinement/context: If the application is not easy to use then it won't be helpful for the user.
Mitigation/monitoring: The end user demands are considered and the application will be developed based on that.
Management/contingency plan/trigger: End user feedback will be taken from time to time so that the app development can be according to those reviews.
Current status: As of 1/31/2020: It will be initiated once the first phase of the application is complete.
Originator: B. Dempsey, L. Johnson, O. Ilano, A. Samuel, S. Singh |  | Assigned: S. Singh

## RIS9
Risk information sheet
Risk ID: RIS9 | Date: 1/31/2020 | Prob: 10% | Impact: Low
Description: In order to implement the requirements of the project as it has been described to us, the implementation of a database would be necessary.
Refinement/context: A database would need to be implemented in order to implement the desired functionality, but the product owner has specified that a database is not necessary.
Mitigation/monitoring: We are currently operating on the assumption that the product owner will not change their mind.
Management/contingency plan/trigger: If the product owner does decide that a database must be implemented, we will work to implement one as efficiently as possible.
Current status: 1/31/20: Product owner has not changed their mind
Originator: B. Dempsey, L. Johnson, O. Ilano, A. Samuel, S. Singh |  | Assigned: B. Dempsey

## RIS10
Risk information sheet
Risk ID: RIS10 | Date: 01/31/2020 | Prob: 10% | Impact: Low
Description: To fit the project into the requirements for personal users we would need to implement user logins.
Refinement/context: We would sample database of users, to allow for individuals to follow certain bands or venues.
Mitigation/monitoring: We are currently requiring our app to be able to follow bands based on the user.
Management/contingency plan/trigger: If the product owner decides that they just want the app to not have personalized information.
Current status: Current requirements still stand.
Originator: B. Dempsey, L. Johnson, O. Ilano, A. Samuel, S. Singh |  | Assigned: A. Samuel